Sprint 1 Planning

Start Date: 14 Nov 2016

Sprint goal: To create simple CRUD feature for customer module

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Sprint Backlog** | **Point** | **Tasks** | **Assigned to** | **Estimated time** |
| Customer Registration | 2 | Create customer table in database | Yi Ting | 1 hours |
| Design add customer UI | Sin En | 2 hours |
| Add input verification to UI page | Sin En | 1 hours  30 minutes |
| Error Message when blank text field | Yi Ting | 1 hours |
| Code controller to save customer data to database | Yi Ting | 5 hours |
| View Customer Information | 1 | Design view customer UI | You Hui | 2 hours |
| Code controller to get specific customer data from database | Jing Wei | 5 hours |
| Update Customer Information | 2 | Design update customer UI | Sin En | 2 hours |
| Add input verification to UI page | Yi Ting | 1 hours |
| Error Message when blank text field | Yi Ting | 1 hours |
| Code controller to retrieve specific customer data from database | Sin En | 5 hours |
| Code controller to update new specific customer data to database | Yi Ting | 5 hours |
| Delete Customer Information | 2 | Design delete customer UI | You Hui | 2 hours |
| Add input verification to UI page | Jing Wei | 1 hours |
| Error message when blank text field | Jing Wei | 1 hours |
| Code controller to retrieve specific customer data from database | You Hui | 5 hours |
| Code controller to delete specific customer data from database | Jing Wei | 5 hours |

Sprint 2 Planning

Start Date: 21 Nov 2016

Sprint goal: To create simple CRUD feature for room module

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Sprint Backlog** | **Point** | **Tasks** | **Assigned to** | **Estimated time** |
| Add New Room Information | 2 | Create room table in database | You Hui | 1 hours |
| Design add room UI | Yi Ting | 2 hours |
| Add input verification to UI page | Yi Ting | 1 hours  30 minutes |
| Error Message when blank text field | You Hui | 1 hours |
| Code controller to save room data to database | You Hui | 5 hours |
| View Room Information | 1 | Design view room UI | Jing Wei | 2 hours |
| Code controller to get specific room data from database | Sin En | 5 hours |
| Update Room Information | 2 | Design update room UI | Jing Wei | 2 hours |
| Add input verification to UI page | Sin En | 1 hours |
| Error Message when blank text field | Sin En | 1 hours |
| Code controller to retrieve specific room data from database | Jing Wei | 5 hours |
| Code controller to update new specific room data to database | Sin En | 5 hours |
| Delete Room Information | 2 | Design delete room UI | Yi Ting | 2 hours |
| Add input verification to UI page | You Hui | 1 hours |
| Error message when blank text field | You Hui | 1 hours |
| Code controller to retrieve specific room data from database | Yi Ting | 5 hours |
| Code controller to delete specific room data from database | You Hui | 5 hours |

Sprint 3 Planning

Start Date: 28 Nov 2016

Sprint goal: To create add, delete, view feature and check out service for booking module

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Sprint Backlog** | **Point** | **Tasks** | **Assigned to** | **Estimated time** |
| Add New Booking Information | 3 | Create booking table in database | Sin En | 1 hours |
| Design add booking UI | Yi Ting | 2 hours |
| Add input verification to UI page | Yi Ting | 1 hours  30 minutes |
| Error Message when blank text field | Yi Ting | 1 hours |
| Code controller to get specific customer data from database | Yi Ting | 5 hours |
| Code controller to get specific room data from database | Sin En | 5 hours |
| Calculation for total price needed to pay | Sin En | 2 hours |
| Code controller to save booking data to database | Yi Ting | 5 hours |
| View Booking Information | 1 | Design view booking UI | You Hui | 2 hours |
| Code controller to get specific customer data from database | You Hui | 5 hours |
| Code controller to get specific booking data from database | Jing Wei | 5 hours |
| Delete Booking Information | 2 | Design delete booking UI | Yi Ting | 2 hours |
| Add input verification to UI page | Sin En | 1 hours |
| Error message when blank text field | Sin En | 1 hours |
| Code controller to retrieve specific customer data from database | Sin En | 5 hours |
| Code controller to delete specific booking data from database | Yi Ting | 5 hours |
| Check Out Room | 3 | Design check out room UI | Jing Wei | 2 hours |
| Code controller to retrieve booking data from database | Jing Wei | 5 hours |
| Code controller to retrieve specific customer data from database | You Hui | 5 hours |
| Code controller to update specific booking data to database | Jing Wei | 5 hours |
| Code controller to update specific room data to database | You Hui | 5 hours |

Sprint 4 Planning

Start Date: 12 Dec 2016

Sprint goal: To make payment module and change room status

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Sprint Backlog** | **Point** | **Tasks** | **Assigned to** | **Estimated time** |
| Make Payment with cash | 3 | Create payment table in database | You Hui | 1 hours |
| Design make payment UI | Jing Wei | 2 hours |
| Add input verification to UI page | Jing Wei | 1 hours |
| Code controller to retrieve specific customer data from database | Yi Ting | 5 hours |
| Code controller to retrieve specific booking data from database | You Hui | 5 hours |
| Error message when blank text field | Jing Wei | 1 hours |
| Calculation of change | Jing Wei | 1 hours |
| Code controller to update specific booking data to database | Yi Ting | 5 hours |
| Code controller to update specific room data to database | You Hui | 5 hours |
| Make Payment with credit card | 2 | Code controller to update specific booking data to database | Jing Wei | 5 hours |
| Code controller to update specific room data to database | Sin En | 5 hours |
| View Payment history | 2 | Design payment history UI | Sin En | 1 hours |
| Code controller to retrieve specific customer data from database | Sin En | 5 hours |
| Code controller to retrieve specific payment data from database | You Hui | 5 hours |